## Open
Last updated: June 11, 2019
PROJECT NAME RISK REGISTER
Risk # | Risk Description | Probability | Impact | Area Affected | Risk Response | Activity to resolve risk (with dates) | Risk Owner | Date Opened | Date Closed | Status
1 | The TITAN project requires a code freeze which would prohibit any changes to MAINSYS and associated systems. That freeze could impact the schedule and costs of some of the ABCD projects. | Low | Low | Schedule Cost | Accept | 2019-05-15: The ABCD team will focus efforts on non-technology initiatives such as the Business Process Review in Vancouver. | PM | 2019-05-01 |  | Open
3 | Procurement backlog could adversely impact the schedule of the ISIS project. | Medium | Medium | Schedule | Mitigate | 2019-06-11: We are in discussions with the Vendor to arrange a trial license. | PM | 2019-05-11 |  | Open
4 | The entire company is upgrading the office desktops to Office 476. With the extensive use of the desktop environments, there could be extra effort and time required to test system components if this deployment is not complete. | Low | Medium | Schedule Cost Scope | Escalate | 2019-05-11: Monitor this deployment and escalate if the timelines don't align with ABCD timelines | PM | 2019-05-11 |  | Open
5 | Stakeholders experience change saturation | Medium | Medium | Schedule | Mitigate | 2019-04-30: Where Change saturation is being experienced by stakeholders: 1) Work with affected stakeholder group to identify appropriate strategy. 2) Adjust release dates of deliverables allowed for by agile process. 3) Present to steering committee for acceptance of resolution | PM | 2019-04-30 |  | Open
6
7
8
9
10

## Closed
Last updated: June 11, 2019
Project Name - Closed Risks
Risk # | Risk Description | Probability | Impact | Area Affected | Risk Response | Activity to resolve risk (with dates) | Risk Owner | Date Opened | Date Closed | Status
2 | Accounting codes have not been finalized and this could impact project schedules. | Medium | Low | Schedule | Mitigate | 2019-06-02: This is now resolved and closed 2019-05-15: Interim solution to use CCM2 budget codes. | PM | 2019-05-01 | 2019-06-02 | Closed
3
4
5
6